## Project Template
Project Template
Project | Hangout |  |  |  |  | Project Manager |  | Dean Vo
Project Start Date |  | 2019-08-26 |  |  |  | Project End Date |  | 2020-05-01
Task |  | Task Type | Task Status | Est SLOC | Actual SLOC | Priority | Assigned To | Assigned Date | Deadline | Estimated Hrs | Start Date | End Date | % Done | Actual Hr.
Configure MongoDB Atlas DB |  | Development | Assigned | -- |  | Medum | Eric | 2019-09-16 | 2019-11-06 | 12 | 2019-09-16 | TBD | 60%
Linode server configuration |  | Development | In-Progress | -- |  | High | Brandon | 2019-09-16 | 2019-10-16 | 8 | 2019-09-16 | TBD | 10%
User sign up |  | Development | In-Progress | -- |  | Medium | Antonio | 2019-09-18 | 2019-10-16 | 8 | 2019-09-18 | TBD | 50%
User authentication |  | Development | In-Progress | -- |  | High | Antonio | 2019-09-11 | 2019-10-09 | 6 | 2019-09-11 | TBD | 40%
Create react project |  | Development | Assigned | -- |  | High | Ashley | 2019-09-23 | 2019-10-16 | 6 | 2019-09-23 | TBD | 90%
Home page front-end |  | Development | Created | -- |  | Medium | -- | [5 empty] | 10%
User profile generation + editing |  | Development | Assigned | -- |  | Medium | Dean | [5 empty] | 30%
Total Hours Spent |  | 0
Project Progress |  | 41.4286 | %

## Default Fields
Select Project | Select Task | Select Status | Select Priority | Select Project Manager | Select Resource | % Done | Task Type
Hangout | Server Configuration | Created | Low | Dean Vo | Brandon | 10% | Bug
-- | Database Setup | Assigned | Medium | -- | Eric | 20% | Business Strategy
-- | UI Design | In-Progress | High | -- | Ashley | 30% | Product Planning
-- | System Architecture | Completed | -- | -- | Antonio | 40% | Development
-- | Secure User Login | Resolved | -- | -- | Dean | 50% | Enhancement
-- | Front-End Frameworks | Re-Opened | -- | -- | -- | 60% | Customer Issue
-- | Account Creation | -- | -- | -- | -- | 70% | Application Structure
-- | Domain Registration | -- | -- | -- | -- | 80% | --
-- | UI Wireframes | -- | -- | -- | -- | 90% | --
-- | Configure MongoDB Atlas DB | -- | -- | -- | -- | 100% | --
User authentication
Linode server configuration
Create react project
User sign up
Home page front-end
User profile generation + editing